NAIA

Fundraising Strategy & 8-Week Plan

Pre-seed £500k SEIS/EIS · Target close within ~8 weeks · Prepared July 2026

heynaia.ai

# The strategy in one page

You are raising a £500k pre-seed on a tight timeline, pre-launch, in the UK. That shapes three decisions:

- 1. Sell traction-in-motion, not just vision.  You will not have months of revenue to point to, so the round is won on founder, working product, a proven category (validated by a US comparable), and — critically — early demand signal you manufacture during the raise itself. Run the traction sprint and the fundraise in parallel; do not wait for one to finish the other.

- 2. Make SEIS/EIS the centre of gravity.  A £500k UK pre-seed is structurally cheaper for investors because of 50% (SEIS) / 30% (EIS) tax relief. This is your biggest lever. Get HMRC advance assurance first, then lead every angel conversation with it.

- 3. Anchor first, then fill fast.  Land one anchor cheque from an active SEIS fund (e.g. SFC Capital / Fuel) to set terms and de-risk the round, then fill the rest with warm angels running as overlapping, time-boxed conversations to create genuine momentum.

Reality check: closing £500k in ~8 weeks is aggressive but achievable for a warm, SEIS-eligible, product-ready pre-seed. If the clock is truly hard (<2 months of runway), the fastest path is a first close on warm angels + one anchor, then a rolling second close — don't hold the whole round hostage to a single lead.

# Before you email a single investor (Week 0-1 pre-work)

Momentum dies when you have to stop mid-raise to build a document an investor asked for. Prepare all of this up front:

- HMRC SEIS/EIS advance assurance:  apply now. It's the single most requested thing from UK angels and can take a couple of weeks — start the clock immediately (SeedLegals or an accountant can file it).

- Materials:  the accompanying pitch document, plus a 10-12 slide deck cut from it (deck = the pitch doc, compressed to headlines + one chart per slide).

- Data room:  a single shareable folder: deck, one-pager, pitch doc, financial model / cap table, product demo (a 2-minute Loom of NAIA working), founder bio, and the SEIS/EIS assurance once granted.

- Instrument:  decide SAFE-style vs. ASA vs. light priced round with a startup lawyer. For the SEIS/EIS tax-relief portion use an ASA or priced round (standard SAFEs are not automatically SEIS/EIS-qualifying).

- Terms clarity:  valuation cap / price, minimum cheque (e.g. £10k), target first close, and use of funds. Investors will ask in the first meeting.

- Outreach templates:  a 2-3 line cold email, a warm-intro-request template, and a follow-up template. Personalise the first line only.

Do the traction-sprint setup in the same window: build the eligibility-quiz landing pages and wire the Instagram ad account so spend can start in Week 1.

# The two workstreams, run in parallel

## Workstream A — Traction sprint (proof you buy demand)

- Launch:  2-3 procedure/destination landing pages behind an eligibility quiz that captures the lead.

- Spend:  a modest, controlled Instagram/paid-social budget into the quiz. Optimise for cost-per-qualified-enquiry, not clicks.

- Supply:  sign 3-5 clinics on a commission LOI ('qualified patients, zero upfront cost') so enquiries have somewhere to go.

- Measure:  CAC, enquiry→eligible→approved funnel, and the first booking(s). These numbers ARE the pitch update each week.

## Workstream B — The raise

- Pipeline:  work the accompanying Investor Target List top-down: Tier A + your own angel network first.

- Cadence:  batch outreach weekly so conversations overlap and you can honestly say 'we're in active conversations and moving to a first close.'

- Warm intros:  for every cold target, find the warm path first. Ask each investor who says no for two intros.

- Discipline:  update the tracker after every touch; use the Pipeline Math tab to know how many conversations you still need.

# The 8-week plan

| Week | Traction sprint (A) | The raise (B) | Milestone |
| --- | --- | --- | --- |
| 1 | File SEIS/EIS advance assurance. Ship quiz landing pages. Launch first IG ads. | Finalise deck, one-pager, data room, instrument & terms with lawyer. | Materials + ad spend live |
| 2 | Tune ads to cost-per-qualified-enquiry. Outreach to first clinics. | Map warm intros for every Tier A target. Request intros. Book SFC Capital + Fuel conversations. | Warm intro requests out |
| 3 | First qualified enquiries flowing. 1-2 clinic LOIs signed. | First investor meetings (Tier A + warm angels). Send deck + demo Loom after each. | First meetings held |
| 4 | Push first enquiries through eligibility → docs → clinic review. | Second meetings. Circulate the SEIS anchor conversation to create signal. Follow up relentlessly. | Anchor in diligence |
| 5 | Aim for first surgeon-approved booking(s). Publish a weekly metrics update. | Convert anchor to verbal yes. Use it to accelerate angels ('lead is in, filling the round'). | Anchor verbal yes |
| 6 | First booking / first escrowed deposit. Nail down CAC + conversion numbers. | Collect angel commitments toward the first-close target. Send docs to committed investors. | First-close committed |
| 7 | Keep spend + bookings running as live proof during signing. | FIRST CLOSE: sign + collect from anchor + committed angels. Issue SEIS/EIS paperwork. | FIRST CLOSE ✔ |
| 8 | Package results into a one-page traction update. | Rolling second close on remaining pipeline. Bank the round. Send close note + thank-yous. | Round closed |

If the timeline compresses further, collapse to a single goal: anchor + warm angels to a first close by Week 5-6, and let everything else be the rolling second close.

# How to run investor conversations

- First touch:  2-3 sentence email or intro, then a 20-30 min call. Don't send the full deck cold — send the one-pager + demo Loom, save the deck for/after the call.

- The meeting:  story (problem→NAIA→why now), live demo, the traction sprint numbers so far, the ask and terms, then Q&A. End every call with a specific next step and a date.

- Follow up:  within 24 hours, every time, with the deck, the data-room link, and the one new proof point since you last spoke. Speed signals momentum.

- Create urgency honestly:  when someone commits, ask for the cheque size, then ask 'who else should I be talking to?' Warm intros from investors convert far better than cold.

- Handle no's:  a no is a gift if it comes with two intros or one clear reason. Log the reason; if you hear the same objection three times, fix it in the deck.

## Objections you'll hear (pre-launch) and how to answer

| Objection | Your answer |
| --- | --- |
| “No traction yet.” | “That's exactly what this round funds — and here's the CAC and funnel data from the ads we're already running.” |
| “Is this just cosmetic tourism?” | “It's a trust-and-coordination platform for a proven, growing category — with escrow, audit, and aftercare no facilitator offers.” |
| “How is this defensible?” | “Proprietary conversation data, two-sided liquidity, verified supply, and outcome data that compounds with every case.” |
| “Clinical/regulatory risk?” | “NAIA never gives clinical advice — every medical and financial judgement is deferred to the surgeon by design.” |
| “Why you?” | [Your founder-market fit, in one sentence — and point at the working product as proof of execution.] |

# Risks to the plan & mitigations

- Warm-intro coverage:  if warm intros are thin, the raise slows. Mitigate by front-loading your own angel network (A* archetypes) and asking every conversation for two intros.

- SEIS/EIS timing:  if advance assurance is delayed, angels hesitate. Mitigate by filing in Week 0 and using an ASA that converts on assurance.

- Traction not landing fast enough:  if IG CAC is high early, don't panic — show the trend and the funnel; a credible path matters more than a perfect number at pre-seed.

- Anchor doesn't close:  if no single lead emerges, use a first close on warm angels to build momentum rather than waiting.

- Runway pressure:  if runway is truly <2 months, run a bridge/first-close in parallel and talk to founders about emergency angel cheques; protect optionality.

# Your first five actions (this week)

- 1.  File SEIS/EIS advance assurance (SeedLegals or accountant).

- 2.  Cut the 10-12 slide deck from the pitch document and record a 2-minute NAIA demo Loom.

- 3.  Ship the eligibility-quiz landing pages and switch on a small Instagram ad budget.

- 4.  Open the Investor Target List; for every Tier A name, write down the warm-intro path and send the first five intro requests.

- 5.  Book the SFC Capital and Fuel Ventures conversations — your anchor candidates.

Companion documents: the Investor Pitch (the story + the ask) and the Investor Target List (who to contact, and the pipeline math for how many). Work all three together.