## Summary
Oia — Status Summary
Auto-counts from the Tracker tab · reviewed 2026-07-08
By status
Done
In progress
Outstanding
Total items
% complete
Outstanding by priority
High
Medium
Low

## Tracker
Oia — Build Tracker
Last reviewed: 2026-07-08 · Status verified against live code + production DB
ID | Area | Item | Status | Priority | Notes / Verification | Updated
INF-01 | Infra & Identity | NIA → Oia rename (final); domain heyoia.com secured | Done |  | Confirmed by Ida 2026-07-03 | 2026-07-08
INF-02 | Infra & Identity | Repo github.com/idatink/oia (idatink account active) | Done |  | Old repo kept as reference remote | 2026-07-08
INF-03 | Infra & Identity | Vercel team oiaai: oia-web + oia-dashboard | Done |  | Both build clean | 2026-07-08
INF-04 | Infra & Identity | Neon Postgres production DB | Done |  | Live; queried this session | 2026-07-08
INF-05 | Infra & Identity | Vercel Blob store (private, London/LHR1, OIDC) | Done |  | oia-dashboard-blob | 2026-07-08
INF-06 | Infra & Identity | Fly app oia-whatsapp (OpenClaw runtime) | Done |  | WA +447752991023 healthy; inbound→reply proven live | 2026-07-08
AGT-01 | Agent | Two-mode persona live: patient intake + clinic negotiation | Done |  | SOUL/IDENTITY/AGENTS/MEMORY, Oia-branded | 2026-07-08
AGT-02 | Agent | 5 skills wired | Done |  | create-inquiry, get-recommendations, smart-match, submit-quote, upload-photo | 2026-07-08
AGT-03 | Agent | Hard price-grounding on web concierge | Done |  | Refuses to invent prices (web only) | 2026-07-08
AGT-04 | Agent | Anonymous-first intake (Decision A3) + link-session merge | Done |  | Web + WhatsApp history unify under one patient | 2026-07-08
AGT-05 | Agent | Web concierge wired to Oia soul end-to-end | Done |  | Confirmed working | 2026-07-08
SM-01 | SmartMatch | Engine: interpret → filter → score → persist | Done |  | Deterministic + explainable reasons | 2026-07-08
SM-02 | SmartMatch | Provider/treatment data seeded in production | Done |  | 45 surgeons (TR), 426 treatments (163 matchable), 27 categories | 2026-07-08
SM-03 | SmartMatch | Wired into live intake; shortlists persisted | Done |  | 3 real ProviderMatch records; latest 2026-07-08 | 2026-07-08
PHO-01 | Patient Photos | Private upload pipeline (dashboard → signed display) | Done |  | Vercel Blob | 2026-07-08
CKP-01 | Cockpit | Lead alerts with AI score + rationale (journey P8) | Done |  | LIVE | 2026-07-08
CKP-02 | Cockpit | Consultation booking (P9) | Done |  | LIVE | 2026-07-08
CKP-03 | Cockpit | Deposit → CONFIRMED (P11) | Done |  | LIVE | 2026-07-08
CKP-04 | Cockpit | Pre-op scheduling (P12) | Done |  | LIVE | 2026-07-08
CKP-05 | Cockpit | Today's Arrivals (P13) | Done |  | LIVE | 2026-07-08
CKP-06 | Cockpit | Surgery-day booking management (P14) | Done |  | LIVE | 2026-07-08
CKP-07 | Cockpit | Matched Surgeons panel | Done |  | LIVE | 2026-07-08
CKP-08 | Cockpit | Real-time WhatsApp conversation sync | Done |  | Drop-off visibility | 2026-07-08
CKP-09 | Cockpit | Coordinator outbound to a clinic | Done |  | Proven ONCE, manual trigger (fly ssh) | 2026-07-08
WEB-01 | Web Redesign | Sanctuary homepage + Oia icon library + 13 app screens | Done |  | LOCAL-ONLY branch; not shipped | 2026-07-08
AGT-06 | Agent | Coordinator REPLY handling / C1–C4 negotiation gate | Outstanding | High | Clinic replies not handled; no auto back-and-forth or quote logging | 2026-07-08
AGT-07 | Agent | Automate outbound trigger (patient selects → Oia contacts clinic) | Outstanding | High | Currently manual fly ssh | 2026-07-08
AGT-08 | Agent | Price table + grounding on WhatsApp | Outstanding | Medium | Web done; WhatsApp not | 2026-07-08
AGT-09 | Agent | Single-source soul in DB | Outstanding | Medium | So Training Lab edits persist on Vercel; currently disk-only | 2026-07-08
SM-04 | SmartMatch | Add GB / non-Turkey providers | Outstanding | Medium | 45 surgeons all TR; UK patients always matched abroad | 2026-07-08
SM-05 | SmartMatch | Per-technique matching (populate ProviderTreatment) | Outstanding | Medium | Currently cluster-level only | 2026-07-08
SM-06 | SmartMatch | Add price / portfolio / availability to ranking | Outstanding | Low | Ranks on accreditation + specialism + reviews only | 2026-07-08
JNY-01 | Journey Gaps | Treatment proposal tool in dashboard (P10) | Outstanding | Medium | Currently off-platform | 2026-07-08
JNY-02 | Journey Gaps | Post-op scheduled reminders (P15) | Outstanding | Medium | No automation | 2026-07-08
JNY-03 | Journey Gaps | Case closure flow (P16) | Outstanding | Medium | Outcome capture + review request | 2026-07-08
JNY-04 | Journey Gaps | Dual-sided live logging (P1) | Outstanding | High | Stream patient + coordinator threads to dashboard real-time | 2026-07-08
OPS-01 | Housekeeping / Risk | Point heyoia.com → oia-web | Outstanding | High | DNS | 2026-07-08
OPS-02 | Housekeeping / Risk | Rotate Anthropic API key + WHATSAPP_INTAKE_SECRET | Outstanding | High | Both appeared in a transcript | 2026-07-08
OPS-03 | Housekeeping / Risk | Confirm Neon region is EU (GDPR) | Outstanding | Medium |  | 2026-07-08
OPS-04 | Housekeeping / Risk | Verify photo upload under OIDC Blob | Outstanding | Medium | Or confirm BLOB_READ_WRITE_TOKEN path | 2026-07-08
OPS-05 | Housekeeping / Risk | Ship web redesign (delete /screens + /icon-lab first) | Outstanding | Medium |  | 2026-07-08
OPS-06 | Housekeeping / Risk | Rename residual 'Nia' internals | Outstanding | Low | @nia/* packages, create_nia_inquiry, repo dir | 2026-07-08
OPS-07 | Housekeeping / Risk | Commit/clean pending working-tree changes | Outstanding | Low | AGENTS.md tweak, fly.toml, oia-redesign.patch | 2026-07-08
WEB-02 | Web | Sanctuary in-app imagery pass (surgeon/clinic/reference/results photos, central IMG map) | In progress | Medium | Awaiting Ida review of before/after sheet; local only, not deployed | 2026-07-08